## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US01 | A feature that allows users to upload contract text files into the system. | Must | None | Sravani Rongali | Done
S1 | S1 | US02 | Load the Dataset.txt file and check if the AI model (LLM) is working correctly. | Must | None | Sravani Rongali | Done
S2 | S2 | US03 | Extract important clauses from uploaded contract files and store them in CSV/JSON. | Must | US02 | Sravani Rongali | Done
S2 | S2 | US04 | Scan contracts and highlight risks based on matching regulation keywords. | Must | US03 | Sravani Rongali | Done
S2 | S2 | US05 | Allow users to ask questions about regulations and get answers using the AI model. | Must | US02 | Sravani Rongali | Done
S3 | S3 | US06 | Update existing contract files using the latest regulation changes and create new versions. | Must | US04 | Sravani Rongali | Done
S3 | S3 | US07 | Generate amendment suggestions based on the relevant regulations. | Should | US06 | Sravani Rongali | Done
S4 | S4 | US08 | Integrate all the milestones with streamlit | Must | US07 | Sravani Rongali | Done
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 47 | 20 | 21 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | T1.1 | Create required directories (Data/Contracts/Regulations) | 2025-10-20 | 2025-10-27 | Sravani Rongali | Coding | Done | 2 | Day 1: 1; Day 2: 1; Day 3: 0
US-01 | T1.2 | Implement file uploader (Streamlit) | 2025-10-20 | 2025-10-27 | Sravani Rongali | Coding | Done | 3 | Day 1: 1; Day 2: 2; Day 3: 0
US-01 | T1.3 | Integrate file saving & listing in sidebar | 2025-10-20 | 2025-10-27 | Sravani Rongali | Coding | Done | 2 | Day 1: 1; Day 2: 1; Day 3: 0
US-06 | T1.4 | Create sidebar navigation pages | 2025-11-25 | 2025-12-02 | Sravani Rongali | Coding | Done | 2 | Day 1: 1; Day 2: 1; Day 3: 0
US-02 | T2.1 | Implement milestone1_load_preprocess() | 2025-11-01 | 2025-11-07 | Sravani Rongali | Coding | Done | 4 | Day 1: 2; Day 2: 2; Day 3: 0
US-02 | T2.2 | Integrate LLM test with GROQ/OpenAI | 2025-11-01 | 2025-11-07 | Sravani Rongali | Coding | Done | 2 | Day 1: 1; Day 2: 1; Day 3: 0
US-02 | T2.3 | Implement milestone2_clause_extraction() | 2025-11-01 | 2025-11-07 | Sravani Rongali | Coding | Done | 5 | Day 1: 2; Day 2: 2; Day 3: 1
US-02 | T2.4 | Save CSV & JSON clause outputs | 2025-11-01 | 2025-11-07 | Sravani Rongali | Coding | Done | 2 | Day 1: 1; Day 2: 1; Day 3: 0
US-03 | T3.1 | Implement check_risks() | 2025-11-10 | 2025-11-17 | Sravani Rongali | Coding | Done | 4 | Day 1: 1; Day 2: 2; Day 3: 1
US-04 | T3.2 | Implement apply_updates() | 2025-11-10 | 2025-11-17 | Sravani Rongali | Coding | Done | 5 | Day 1: 2; Day 2: 2; Day 3: 1
US-04 | T3.3 | Add regulation sample creators | 2025-11-10 | 2025-11-17 | Sravani Rongali | Coding | Done | 2 | Day 1: 1; Day 2: 1; Day 3: 0
US-05 | T4.1 | Implement QA system (run_qa_system) | 2025-11-20 | 2025-11-24 | Sravani Rongali | Coding | Done | 5 | Day 1: 2; Day 2: 2; Day 3: 1
US-06 | T4.2 | Add Streamlit pages (Clause, Risk, Updates, Amendments) | 2025-11-25 | 2025-12-02 | Sravani Rongali | Coding | Done | 5 | Day 1: 2; Day 2: 2; Day 3: 1
US-06 | T4.3 | Remove unnecessary sidebar path display | 2025-11-25 | 2025-12-02 | Sravani Rongali | Coding | Done | 1 | Day 1: 1; Day 2: 0; Day 3: 1
US-06 | T4.4 | Test entire UI flow end-to-end | 2025-11-25 | 2025-12-02 | Sravani Rongali | Testing | Done | 3 | bar: Day 1 to Day 3
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Difficulty setting up folder structure for Data, Contracts, Regulations | Created fixed BASE_DIR paths and added ensure_dirs() to auto-create folders
Sprint 1 | Day 2 | API keys not loading from .env file | Added load_env_keys() function using dotenv
Sprint 1 | Day 3 | Dataset failing due to inconsistent spacing | Added regex cleanup and chunking in milestone1_load_preprocess()
Sprint 2 | Day 6 | LLM clause extraction response not giving proper JSON | Implemented _safe_parse_json_like() and extract_json() for safe parsing
Sprint 2 | Day 8 | Risk scoring inaccurate for some clauses | Added rule_based_risk() with keyword conditions
Sprint 2 | Day 10 | Large contract text causing slow response | Added text[:4000] limitation in prompt to optimize
Sprint 3 | Day 14 | Regulations folder empty causing empty suggestions | Added mock_fetch_regulation() to simulate new regulations
Sprint 3 | Day 16 | Matching regulations to contracts not working | Improved keyword detection in check_risks()
Sprint 3 | Day 18 | Contract update files not saving new versions | Fixed file versioning logic with _v{version}.txt format
Sprint 4 | Day 20 | Scheduler thread not running properly | Started daemon thread for scheduler(regs)
Sprint 4 | Day 23 | Streamlit UI showing unwanted left-side paths | Removed sidebar project directory display from UI
Sprint 4 | Day 25 | Large LLM answers slowing UI rendering | Added 3–5 sentence limit + optimized QA context retrieval

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 – Backend Foundations | 2025-10-20 | 2025-10-27 | Sravani | Start documenting each module after implementing | Stop working without a clear plan | Continue modular coding | Created a structured folder layout and added comments + README for each module
2 | Sprint 2 – LLM Integration | 2025-11-01 | 2025-11-07 | Sravani | Start testing LLM outputs with sample regulatory documents | Stop relying on single prompt format | Continue improving prompt templates | Added validation methods and JSON formatting checks for consistent LLM output
3 | Sprint 3 – Compliance Rule Engine (Risk Scoring) | 2025-11-10 | 2025-11-17 | Sravani | Start writing reusable scoring functions | Stop hardcoding policies | Continue reviewing regulatory datasets | Implemented dynamic compliance score calculator + mapping rules
4 | Sprint 4 – Streamlit Integration | 2025-11-20 | 2025-11-27 | Sravani | Start focusing on UI clarity and navigation | Stop adding unnecessary content in left sidebar | Continue client testing | Cleaned UI, removed unnecessary paths, optimized upload & display flow
5 | Sprint 5 – API, Evaluation, Final Testing | 2025-11-29 | 2025-12-02 | Sravani | Start automated testing for clause extraction | Stop delaying bug fixes | Continue documenting changes | Fixed file parsing issues, improved performance, added API key testing flow